INTERNAL AUDIT AGENCY

ANNUAL PERFORMANCE REPORT FOR THE PERIOD

JANUARY - DECEMBER 2022

`

Contents

PART ONE:.........................................................................................................................................2 1.0 PROFILE OF THE AGENCY ..............................................................................................................2 VISION:......................................................................................................................................................2 MISSION:...................................................................................................................................................2 CORE FUNCTIONS:.....................................................................................................................................2 POLICY OBJECTIVES...................................................................................................................................3 PART TWO:........................................................................................................................................4 2.0 KEY ACHIEVEMENT, REFORMS AND SUSTAINABLE DEVELOPMENT GOALS (SDGs) OF THE AGENCY .4 2.1 KEY ACHIEVEMENTS............................................................................................................................4 PART THREE:....................................................................................................................................12 3.0 FINANCIAL PERFORMANCE ...............................................................................................................12 PART FOUR:.....................................................................................................................................13 4.0 CHALLENGES ..............................................................................................................................13 PART FIVE:.......................................................................................................................................14 5.0 WAY FORWARD..........................................................................................................................14 5.1 RECOMMENDATION AND CONCLUSIONS ....................................................................................15 5.1.1 RECOMMENDATIONS.....................................................................................................................15 5.1.2 CONCLUSION..................................................................................................................................15 APPENDIX I-STATUS OF IMPLEMENTATION OF PLANNED PROGRAMMES ..........................................16 APPENDIX II - SYSTEMIC ISSUES ........................................................................................................25 APPENDIX III: Details of Training Provided for the period 1st January to 0th December 2022................27

Internal Audit Agency 1 2022 3rd Quarter Performance Report

PART ONE:

1.0 PROFILE OF THE AGENCY

The Government of the Republic of Ghana by the Internal Audit Agency Act, 2003 (Act  658) established the Internal Audit Agency as an apex oversight body to co-ordinate,  facilitate and provide quality assurance for internal audit activities within Ministries,  Departments, and Agencies (MDAs) and Metropolitan, Municipal and District Assemblies  (MMDAs). The Agency is part of the Office of Government Machinery (OGM).

VISION:

The Agency's vision is to be a centre of excellence in promoting best practices in internal  auditing with integrity and professionalism.

MISSION:

The Mission of the Agency is to exercise oversight responsibility over internal audit  practice in the public service by coordinating, facilitating, and setting standards; providing quality assurance, and supporting capacity building for good corporate governance, and  effective risk management.

CORE FUNCTIONS:

Section 3 of the Act provides the functions of the Agency as follows:

1) Set standards and procedures for the conduct of internal audit activities in the MDAs  and MMDAs.

2) Ensure that;

• financial, managerial, and operating information reported internally and externally is  accurate, reliable, and timely;

• the financial activities of MDAs and MMDAs comply with laws, policies, plans,  standards, and procedures;

• national resources are adequately safeguarded;

• national resources are used economically, effectively, and efficiently; • plans, goals, and objectives of MDAs and MMDAs are achieved; and • risks are adequately managed in the MDAs and MMDAs.

3) Without limiting subsections (1) and (2), the Agency shall

Internal Audit Agency 2 2022 3rd Quarter Performance Report

• promote economy, efficiency, and effectiveness in the administration of government  programmes and operations;

• prepare plans to be approved by the Board for the development and maintenance of  an efficient internal audit for the MDAs and MMDAs;

• facilitate the prevention and detection of fraud; and

• provide a means for keeping the MDAs and MMDAs fully and currently informed about  problems and deficiencies related to the administration of their programmes and  operations and the necessity for appropriate corrective action.

4) monitor, undertake inspections and evaluate the internal auditing of the MDAs and  MMDAs.

POLICY OBJECTIVES

The strategic objectives of the Agency are as follows:

• To continuously improve internal audit practice for effective public financial  management.

• To build and strengthen institutional capacity and capability of IAA for value-adding  internal audit practice.

• To re-position internal audit practice in the public service of Ghana for improved  visibility, public acceptability, and support.

Internal Audit Agency 3 2022 3rd Quarter Performance Report

PART TWO:

2.0 KEY ACHIEVEMENT, REFORMS AND SUSTAINABLE DEVELOPMENT GOALS  (SDGs) OF THE AGENCY

This part of the report focuses on the main planned activities undertaken by the Agency  to achieve its mandate and the achievements attained in their execution. It also highlights  on-going reforms and implementation of SDGs by the Agency.

2.1 KEY ACHIEVEMENTS

The Agency made progress in the implementation of its programmes during the period  under review. The following gives details of the achievement;

a) Monitoring the status of internal audit practice in Covered Entities.

A summary of Monitoring of Internal Audit Practice in Covered Entities is captured in the  table below.

Table 2: Summary of Monitoring activities in Covered Entities as at the end of 31st  December, 2022

| Activities | 2021 | January- December 2022 |  |  |  |  |  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
|  | Total | Ministries |  | Departments & Agencies |  | SoEs, Tertiary& Teaching Hospitals |  | MMDAs |  | 2022 Totals |  |  |
|  | l a u t c A | d e t c e p x E | l a u t c A | d e t c e p x E | l a u t c A | d e t c e p x E | l a u t c A | d e t c e p x E | l a u t c A | d e t c e p x E | l a u t c A | % |
| Established IAUs | 594 | 27 | 27 | 136 | 136 | 209 | 208 | 261 | 261 | 633 | 632 | 99 |
| Established Audit Committees | 533 | 27 | 27 | 136 | 115 | 209 | 136 | 261 | 261 | 633 | 539 | 85 |
| Signed Charters | 502 | 27 | 26 | 136 | 124 | 208 | 172 | 261 | 260 | 632 | 582 | 92 |
| Annual Internal Audit Work Plans | 539 | 27 | 26 | 136 | 132 | 208 | 121 | 261 | 253 | 632 | 532 | 84 |
| Quarterly Internal Audit Reports Received | 1,700 | 108 | 87 | 544 | 378 | 832 | 326 | 1,044 | 913 | 2,528 | 1,704 | 67 |
| Quarterly Internal Audit Reports Reviewed | 1,063 | 87 | 52 | 378 | 165 | 326 | 285 | 913 | 350 | 1,704 | 852 | 50 |
| Annual Performance Report Received | - | 27 | 18 | 136 | 67 | 208 | 66 | 261 | 121 | 632 | 272 | 43 |
| Annual Performance Report Reviewed | - | 18 | 18 | 67 | 66 | 66 | 61 | 121 | 121 | 271 | 266 | 98 |

Internal Audit Agency 4 2022 3rd Quarter Performance Report

❖ Implementation of Internal Audit Recommendations

From the reports reviewed over the period under review, a total of 8,005 audit  recommendations were made, bringing the cumulative recommendations to 14,256.  1,156 of the recommendations have been implemented. The outstanding  recommendations as at December, 2022 is therefore 13,100.

The financial value of infractions and the related recommendations implemented as  reported by the Internal Audit Units within the period is 88.31% representing Gh¢485,234,554.47 out of a value of Gh¢549,431,555.24. The outstanding value of  infractions is therefore Gh¢64,197,000.77. The Agency will through follow-ups, pursue  Management of those Covered Entities to ensure full implementation of the outstanding  recommendations.

The table below details the status of implementation of audit recommendations for the  period.

Table 3: Analysis of Status of Implementation of Audit recommendations as at 15/12/2022.

| Details | 2020 | 2021 | 2022 | TOTAL |
| --- | --- | --- | --- | --- |
| Outstanding Recommendations as at 1/01/2022 | 2,247 | 4,004 | - | 6,251 |
| Recommendations made during the year 2022 | - | - | 8,005 | 8,005 |
| Cumulative Recommendations for the year | 2,247 | 4,004 | 8,005 | 14,256 |
| Recommendations Implemented during the year | 121 | 986 | 49 | 1,156 |
| Outstanding recommendations as at 15/12/2022 | 2,126 | 3,018 | 7,956 | 13,100 |

It is recommended that Management of Covered Entities should encourage prompt  submission of the status of implementation of audit recommendations to the Agency. Additionally, the Agency should strictly demand that Audit Committees vigorously pursue  the implementation of audit recommendations and report on same to the Agency  annually.

The Agency will intensify follow ups on implementation of audit recommendations at the  Covered Entities.

❖ Assessment of Systemic control weakness

These are recurring infractions captured in internal audit reports submitted by the IAUs  and reviewed by the Agency. The infractions relate to non-compliance with various laws  and regulations as well as control weakness associated with the operations of the  Covered Entities involved. These infractions have been summarised as follows:

Internal Audit Agency 5 2022 3rd Quarter Performance Report

Summary of the Systemic Issues

i. Procurement – GH¢ 228,329,246.99

ii. Cash Management – GH₵ 178,610,174.76

iii. Payroll- GH₵1,299,100.36

iv. Contract - GH¢921,097,354.28

v. Tax - GH¢47,619,959.44

vi. Others - GH¢460,775,034.58

(Refer to appendix II for details)

❖ Special Follow-Ups on Audit Recommendations

This involves a prompt followed up by the Agency to verify the status of implementation  of audit recommendations received from the Covered Entities. Validation of status of  implementation of recommendations were carried out in Two Hundred and fifty-two (252)  Covered Entities in the 15 regions of the country. The total number of recommendations  made were 3,746, with 1,762 recommendations satisfactorily implemented, representing  47%. The remaining 53% were at various stages of implementation.

b) Meeting with Heads of Internal Audit Units of Covered Entities During the period under review, the Agency held meetings with the Heads of Internal Audit Units in four (4) regional zones.

The meetings provided the heads of the IAUs with orientation and training in the following  areas;

a. Procurement Auditing

b. Construction Auditing

c. Contract Auditing

d. Contemporary Issues in Public Sector Internal Audit Practice

e. Audit Working Papers

Additionally, 103 heads of IAUs selected by the Agency participated in an European  Union (EU) supported PFM Training on Standardized Procurement Audit Framework  (SPAF). The SPAF has been developed under the Technical Assistance to the Ministry  of Finance for the Implementation of the Ghana Public Finance Management Programme,  in collaboration with the Public Procurement Authority, the Internal Audit Agency and the  Ghana Audit Service. The purpose of the Training was to build the capacity of the Internal  Auditors in conducting procurements audit using the SPAF.

Internal Audit Agency 6 2022 3rd Quarter Performance Report

Ernst & Young (EY), the consultants for the project facilitated the Training from 24th August- 9th December, 2022.

c) Implementing programmes under National Anti-Corruption Action Plan (NACAP) During the period under review, the Agency performed the following activities under the  NACAP as a partner in the fight against corruption.

• Established 6 additional Audit Committees for the period under review.

• The Agency also inaugurated 320 existing Audit Committees of Covered Entities  which were reconstituted after the end of the tenure of the independent members.

• The Agency during the year carried out monitoring of 296 Audit Committees in 15  regions across the country.

• Provided training for 323 Audit Committee members on key issues relating to status  of implementation of audit recommendations.

d) Annual Internal Audit Conference

The primary aim of the Annual Internal Conference is to provide a means for keeping the  Covered Entities fully and currently informed about problems and deficiencies related to  the administration of their programmes and operations and the necessity for appropriate  corrective action. It is also meant to provide a platform for continuous sensitization of  managers of sector Institutions and other stakeholders in Protecting National Resources.

The Agency successfully held the 2022 Internal Audit Conference from 16th- 18th August,  2022 in the third quarter. The Conference was held on the theme, “Injecting Fiscal  Discipline for Resource Mobilization and Utilization for Sustainable Development: The  Role of Internal Auditors”.

e) Special Investigation Assignment

Within the period under review, the following assurance services and special Audit  activities were conducted by the Agency:

❖ ESPV exercise

Payroll audit and headcount conducted in nineteen (19) Covered Entities in the Greater  Accra Region leading to the discovery of 143 “missing names” among other irregularities.

Internal Audit Agency 7 2022 3rd Quarter Performance Report

❖ Headcount at the Accra Metropolitan Assembly

A headcount exercise on staff under the Internally Generated Fund (IGF) of Accra  Metropolitan Assembly was carried. Audit recommendations from the exercise have been  implemented.

❖ A special follow-up exercise at the following Entities:

• Ghana Institute of Languages (GIL)

• Ghana Water Company Limited

• Ghana Cocoa Board and all its subsidiaries and divisions

❖ A comprehensive audit of dividend declarations and payments by the Twifo Oil Palm  Plantation (TOPP) Company Limited covering the period 1998 to 2021 payable to  Government.

❖ Comprehensive audit of National Identification Systems Project by the National  Identification Authority (NIA) in partnership with Identity Management System (IMS).

❖ Collaboration with the Economic and Organised Crime Office (EOCO) on further  investigations of financial malfeasance in two (2) Covered Entities.

❖ Referral to and Collaboration with the Office of the Attorney-General on the  prosecution of two (2) persons who were found to have engaged in financial  malfeasance in a Public Institution.

❖ Internal Control assessment being conducted at the Centre for National Culture  (CNC), in the Greater-Accra Region.

f) Improving collaboration with DPs and key Anti-corruption institutions

The Agency during the period under review, collaborated with DPs and key anti corruption institutions to reposition the Agency as important pre-corruption institution.

The Agency also signed three (3) MoUs under the period of review. These MoUs would  promote anti-corruption efforts and integrity through sustained and effective coordination  of state and non- state actors, strategic partnerships and mobilizing citizens and citizen  groups.

The Agency in collaboration with Centre for Local Governance and Advocacy (CLGA)  launched the PFM League Table (PFMLT) at the Accra Metropolitan Assembly on the

Internal Audit Agency 8 2022 3rd Quarter Performance Report

16th of March 2022. The PFMLT is aimed at improving compliance with the internal audit  requirements under the Public Financial Management Act 2016 (Act, 921) and Internal  Audit Laws in Ghana to reduce corruption. It also seeks to improve transparency and  accountability and to ensure value for money in the use of public sector financial  management.

The IAA would be leading the PFMLT while CLGA and other institutions such NDPC,  SIGA, PPA and would be stakeholders. A total of 136 participants attended the launch.

The Agency together with CDD held a two-day workshop to develop a framework for the  operationalization of MOI on District Accountability Index signed by the two institutions.

The GSAM Consortium in collaboration with the Internal Audit Agency (IAA) together with  other stakeholders held a roundtable discussion on mainstreaming of Performance  Auditing at the decentralized level on the 23rd of June 2022 at the Tomreik Hotel. The  objective of the meeting was to discuss policy options and strategies towards the  implementation of the decentralized performance auditing.

During the period under review, the Agency have also submitted a request for vehicle to  World Bank, Ghana and GIZ. This is to strengthen the monitoring of activities.

The Projects units also submitted two (2) requests to World Bank, Ghana and GIZ, for  vehicles to augment the transport system of IAA.

The Agency is developing MoUs with Cocoa Processing Company Limited, SIGA, Ghana  Audit Service. These MOUs are currently at the draft stages.

The Agency is also developing proposal with the European Union (EU) Plans are far advance to implement ERM training with the District Assemblies. Data collection for PFMLT is scheduled in October 2022

g) Guidelines, Directives and Notices to Heads of Covered Entities

In order to ensure effective internal audit practice and to improve internal audit control  within the Covered Entities, the Agency in the 2022 Fiscal year issued guidelines,  directives and notices to Heads of Covered Entities to take action(s) towards injecting  financial discipline in the Public Section, ensure compliance with the Public Financial  Management Act, 2016 (Act 921), the Public Financial Management Regulations, 2019  (L.I.2378), the Public Procurement Act, 2003 (Act 663) and other relevant laws to support  Covered Entities ensure value for money in Public expenditure.

Internal Audit Agency 9 2022 3rd Quarter Performance Report

These directives include the following:

❖ Adoption of Integrated Professional Practice Framework (IPPF) for Public Sector  Internal Auditing in Ghana in line with International Standards.

❖ Mainstreaming ERM into the operations of covered entities to meet International  Standards for Public Sector Internal Auditing.

❖ Validation of ESPV reports by IAUs.

❖ Monitoring implementation of the Expenditure Rationalization and Revenue  enhancement Measures.

❖ Guidelines for preparing and submitting the 2023 RBIA Workplans. ❖ Organization of Emergency meetings by ACs to Implement recommendations in the  2021 Auditor-General’s Report.

❖ Attendance of AC at External Auditors entrance and exit meetings of Covered Entities. h) Publication of Defaulters

The Agency during the period ensured the publication of defaulters for non-submission of  4th Quarter Internal Audit Reports for 2021, Internal Audit Annual Performance Report for  2021 and 1st Quarter Internal Audit Reports for 2022 as well as Annual Risk-Based  Internal Audit (RBIA) Plans for 2022.

i) Corporate Branding Activities

The Agency has published Fifty-one (51) editions of the weekly IAA Internal Newsletter  to inform its stakeholders and staff on activities and events undertaken during the period  under review.

Interviews granted by the Director-General and other members of Management were  brought to the attention of the public by posting them on the website of the Agency. In  addition, issues relating to the Agency published in the print and electronic media were  posted on the Agency’s website and Facebook page.

j) Capacity building and training for staff of IAUs and Management of Covered  Entities

The Agency’s capacity-building effort is aimed at improving the understanding of  Management, staff, and internal auditors of Covered Entities in governance, risk and  control.

During the period under review, training and capacity building was provided for 1,067 public officers from 123 covered entities in Enterprise Risk Management (ERM), Risk-

Internal Audit Agency 10 2022 3rd Quarter Performance Report

Based Internal Auditing (RBIA), Audit Assignment Working Paper Management,  Guidelines to handling Audit queries, Contemporary Internal Audit Practice in Public  Sector, and Information System (IS) Audit. Details of the trainings are shown in Table 3 below.

Table 4: Training Offered to Management, Staff, and Internal Auditors of Covered  Entities

| # | Thematic Areas | Number of Covered Entities |  |  |  |  |  |  | Number of Officers Trained |  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
|  |  | MDAs | MMDAs | SOEs | Tertiary | Auto Body | OHCS | Total | MDAs | MMDAs | SOEs | Tertiary | Auto Body | OHCS | Total |
| 1 | Enterprise Risk Management | 12 | 0 | 1 | 1 |  |  | 14 | 289 | 0 | 36 | 22 |  |  | 347 |
| 2 | Risk-Based Internal Audit | 1 | 0 | 0 | 0 |  |  | 1 | 9 | 0 | 0 | 0 |  |  | 9 |
| 3 | Audit Assignment Working Paper Management | 0 | 104 | 0 | 0 | 1 |  | 105 | 0 | 305 | 0 | 0 | 11 |  | 316 |
| 4 | Audit Committee | 0 | 0 | 0 | 1 | 0 |  | 1 |  |  |  | 10 | 0 |  | 10 |
| 5 | Guidelines to handling Audit queries | 1 | 0 | 0 | 0 | 0 |  | 1 | 18 | 0 | 0 | 0 | 0 |  | 18 |
| 6 | Contemporary Internal Audit Practice in Public Sector |  |  |  |  |  | 1 | 1 |  |  |  |  |  | 18 | 18 |
| 7 | Overview of Information System Audit |  |  |  |  |  |  |  | 204 | 145 |  |  |  |  | 349 |
| TOTALS |  | 14 | 104 | 1 | 2 | 1 | 1 | 123 | 520 | 450 | 36 | 32 | 11 | 18 | 1,067 |

Details of Training Provided for the period under review is attached as Appendix III 2.2 REFORMS

The IAA in 2023 will continue to Pursue the amendment of the Internal Audit Agency Act  2003 (Act 658) to restructure and reposition the agency to support the performance of the  public sector internal audit function and strengthen the independence of the IAUs in the  fight against corruption.

Internal Audit Agency 11 2022 3rd Quarter Performance Report

PART THREE:

3.0 FINANCIAL PERFORMANCE

The financial performance of the Agency during the period under review is summarised  in table 5 below:

Table 5 - Financial Performance

| # | Expenditure Item | 2022 Approved Budget | Released (End of December 2022) | Actual Expenditure | Variance (D) |
| --- | --- | --- | --- | --- | --- |
|  |  | A | B | C | D=A-B |
| 1 | Compensation of Employees |  |  |  |  |
|  | GoG | 6,083,937.00 | 5,587,341.11 | 5,587,341.11 | 496,595.89 |
| 2 | Goods and Services |  |  |  |  |
|  | GoG | 1,900,000.00 | 441,009.90 | 441,009.90 | 1,458,990.10 |
| 3 | CAPEX | 3,862,406.00 | - | - | 3,862,406.00 |
|  | Total | 11,846,343.00 | 6,028,351.01 | 6,028,351.01 | 5,817,991.99 |

Compensation

The Agency’s Budgetary Allocation for Compensation of employees was  GH¢6,083,937.00 for the period under review. A total of GH¢5,587,341.11 was released  and paid to staff as salaries and allowances for the period representing 91.84% of the  Compensation of employees.

Goods and Services

Releases amounting to GH¢441,009.90 was approved for Goods and Services for the  Agency for the period under review representing 23.21% of the Goods and Service allocation.

Capital Expenditure

An amount of GH¢3,862,400.00 has been approved by the Office of the President as  CAPEX for the Agency for the year 2022.

Internal Audit Agency 12 2022 3rd Quarter Performance Report

PART FOUR:

4.0 CHALLENGES

The Agency, in the implementation of its work plan during the period January to December 2022 encountered the following challenges.

a) Budget constraint and logistical challenge

The Agency’s approved budget over the years has been woefully inadequate to support  its operations. This coupled with the lack of mandate to mobilize internally generated funds  hampers its smooth operations.

b) Low/Uncompetitive Conditions of Service for the staff of IAA

Low salaries and uncompetitive Conditions of Service for Staff of the Internal Audit Agency compared with that of similar institutions in the Public Sector continue to  demotivate Staff of the Agency.

c) Limitation in the independence and objectivity of the Internal audit function. Public Sector Internal Auditors are employees of the respective Covered Entities, and as  a result, budgets of the Internal Audit Units form part of the Budgets of these Covered  Entities, this makes them solely dependent on the entities to perform the internal audit  function, this usually impairs their independence and hence their objectivity.

Additionally, the appointment, transfer, removal, or replacement of internal auditors  without written approval from the Agency continues to affect the work of the agency.

d) Non-Forwarding of the Agency’s Annual Report to Parliament. The Agency’s annual report since 2006 has been submitted to the Office of the President  but is yet to be forwarded to Parliament for consideration as mandated by Section 23 (2)  of the Internal Audit Agency Act 2003, Act 658. Parliament has started an engagement  with the Agency to support them in discussing the Annual Audit Committee reports of  Covered Entities.

Internal Audit Agency 13 2022 3rd Quarter Performance Report

PART FIVE:

5.0 WAY FORWARD

The Internal Audit Agency in the second half of 2022 will focus on contributing towards  Government policy of good governance and accountability as well as implementing its  Strategic Plan to achieve the stated objectives. The Agency will:

a. Pursue the amendment of the Internal Audit Agency Act 2003 (Act 658) to restructure  and reposition the agency to support the performance of the public sector internal  audit function and strengthen the independence of the IAUs in the fight against  corruption.

b. Publish names of public institutions failing to submit relevant quarterly internal audit  reports required by the PFM Act, 2016 (Act 921).

c. Conduct nationwide payroll audit in accordance with the Ministry of finance  expenditure rationalization measure in eliminating ghost names from the public sector  payroll.

d. Operationalized activities in relation to the publication of the Public Financial  Management League Table (PFMLT)

e. Facilitate a revision of the guidelines on effective functioning of Audit Committees to  rationalize the restructuring and make the audit committees viable, functional and  effective.

f. Support public sector institutions to develop and implement standard ERM systems in  the form and manner required by the PFM Act (Act 921).

g. Continue with the monitoring and evaluation of internal audit practice in Covered  Entities.

h. Continue to provide advice and assurance services to Government through the MoF. i. Work with the Auditor-General and EOCO to reduce irregularities and infractions  reported annually through early warning signals and sound control systems.

Internal Audit Agency 14 2022 3rd Quarter Performance Report

5.1 RECOMMENDATION AND CONCLUSIONS

5.1.1 RECOMMENDATIONS

The following recommendations have been made to address challenges identified in the  implementation of the Agency’s plan programmes within the Annual Workplan:

1. Adequate budget allocations should be given to the Agency in order to execute its  mandate effectively.

2. The Heads of Civil and Local Government Services should always seek written  approval from the Director General of the IAA prior to the transfers, replacements and appointments of Heads of Internal Audit Units as mandated by the PFM Act.

3. The Agency should intensify follow-ups to Covered Entities on the status of the  implementation of audit recommendations.

4. The Agency will liaise with the Ministry of Finance to determine the appropriate  sanctions for Covered Entities defaulting in the various submission to the Agency.

5.1.2 CONCLUSION

The Agency made significant progress in executing its mandate in spite of the challenges encountered. It is the Agency’s expectation that its 2022 approved budget will be released  timeously and, in its entirety, to enable the Agency carry out its work plan for 2022.

Internal Audit Agency 15 2022 3rd Quarter Performance Report

APPENDIX I-STATUS OF IMPLEMENTATION OF PLANNED PROGRAMMES

| SN | SUB PROGRAMME | ACTIVITIES | BASELINE-2021 | OUTPUT INDICATORS | STATUS | OUTCOME | REMARKS |
| --- | --- | --- | --- | --- | --- | --- | --- |
| 1 | Field Operations | Review of Internal Audit Charters | 94 Internal Audit Charters received and reviewed. | 106 additional Internal Audit Charters are expected to be received and reviewed | 80 additional Internal Audit Charters received and reviewed | Provide quality assurance on good corporate governance, and effective risk management. | Exceeded expectation |
|  |  | Review of Annual Risk-Based Internal Audit Plans. | 539 Annual Internal Audit Work Plans received and reviewed. | 632 Annual Internal Audit Work plans are expected to be received and reviewed | 532 internal audit plans have been received and reviewed for the period under review. The Agency is monitoring the adherence to the submitted Plans. Letters have also been sent to defaulting IAUs to submit their plans. |  |  |
|  |  | Review of Quarterly Internal Audit Reports. | 1,063 Quarterly Internal Audit Reports received and reviewed. | A total of 2,528 Quarterly Internal Audit Reports expected to be received and reviewed | 852 internal audit reports reviewed out of a total of 1,704 received. |  | Lack of adequate staff and Computers. |
|  |  | Monitoring of Audit Committees activities. | 5 Audit Committees were monitored as at the 3rd Quarter | 500 out of 513 ACs would be monitored | 296 Audit Committees were monitored to assess their performance and report submitted. | Improvement in compliance with laws, policies, plans, standards and procedures; and improvement in implementation of audit recommendations | Lack of funding. |
|  |  | Review of Annual Audit Committees’ reports. | 52 Annual AC Reports received and reviewed | 513 Annual Audit Committees’ reports received and reviewed. | Audit Committees of 461 Covered Entities submitted Annual Audit Committee Reports for 2021 within the period under review. One hundred and twenty-two out of the 461 Audit Committees Reports have been rejected for being irregular because the Annual Statements contained therein were not endorsed by the Sector Minister. Heads of Covered Entities have been requested to secure the sector Minister’s endorsements and resubmit the reports. |  |  |

Internal Audit Agency 16 2022 3rd Quarter Performance Report

| SN | SUB PROGRAMME | ACTIVITIES | BASELINE-2021 | OUTPUT INDICATORS | STATUS | OUTCOME | REMARKS |
| --- | --- | --- | --- | --- | --- | --- | --- |
|  |  | Facilitate the establishment and formation of Audit Committees. | 533 ACs established in covered entities. | 40 additional ACs expected to be established. | 6 additional audit committees established. |  |  |
|  |  | Bi-annual meeting with Heads of IAUs. | Several meetings were held in four (4) zones (332 participants) | Two (2) Meetings expected to be organised | One (1) nationwide meeting with all Heads of IAUs from 4 regional zones was organized. | Build capacity of Covered Entities on Governance, Risk and Control |  |
|  |  | Conduct quarterly Activities under NACAP and Submit report to CHRAJ. | Quarterly NACAP activities was conducted, and report submitted to CHRAJ and Minister of Finance | Four (4) quarterly NACAP activities expected to be conducted and Report Submitted to CHRAJ. | Quarterly NACAP activities for the quarters conducted and report submitted to CHRAJ and Minister of Finance. | To fight against corruption and the promotion of national development |  |
|  |  | Conduct Follow up on status of implementation of internal Audit recommendations. | 143 audit recommendations out of 9,978 were implemented from follow-up exercise carried out in 22 Covered Entities. Out of GH¢866,542,947.48 being the total value of the infractions and the accompanying recommendations made, we observed Gh¢387,003,609.53 have been rectified | Number of internal audit recommendations implemented on the account of follow ups. | 1,156 audit recommendations out of 14,256 outstanding recommendations from the beginning of the year 2022 to the period were implemented. | Improvement in compliance with laws, policies, plans, standards, and procedures; and improvement in implementation of audit recommendations |  |
|  |  |  |  | Financial value of recommendations implemented on the account of follow ups | Out of Gh¢549,431,555.24 being the total value of the infractions and the accompanying recommendations made from the quarterly internal audit report, Gh¢485,234,554.47 have been implemented. |  |  |
|  |  | Organise Annual Internal Audit Conference. | 2022 Annual Internal Audit Conference successful organised | 2023 Annual IAA Conference expected to be organised and Report Submitted | The Agency successfully held the 2022 Internal Audit Conference from 16th - 18th August, 2022 in the third quarter on the theme, “Injecting Fiscal Discipline for Resource Mobilization and Utilization for Sustainable Development: The Role of Internal Auditors”. | Build capacity of Covered Entities on Governance, Risk, Control and effective public financial management. |  |

Internal Audit Agency 17 2022 3rd Quarter Performance Report

| SN | SUB PROGRAMME | ACTIVITIES | BASELINE-2021 | OUTPUT INDICATORS | STATUS | OUTCOME | REMARKS |
| --- | --- | --- | --- | --- | --- | --- | --- |
| 2. | Special Investigations and Internal Audit | Special Audit Assignments undertaken in Covered Entities. |  | Number of Special Audit assignments expected to be conducted and report submitted. | The Agency conducted Special follow ups in the following Covered Entities; Ghana Water Company Limited, Ghana Institute of Languages, Greater Accra Passenger Transport Executive (GAPTE), Pharmacy Council, Ayawaso North Municipal Assembly, Ghana Cocoa Board, Asikuma-Odoben Brakwa District Assembly, Accra Technical University and Ghana Investment Promotion Centre. Special Audit Assignments which were undertaken include the following; • Comprehensive audit of National Identification Systems Project by the National Identification Authority (NIA) in partnership with Identity Management System (IMS). • A comprehensive audit of dividend declarations and payments by the Twifo Oil Palm Plantation (TOPP) Company Limited. |  |  |
|  |  |  |  | Number of assurance and advisory services expected to be conducted and report submitted. | The Agency has undertaken a head count on IGF staff of the Accra Metropolitan Assembly. Additionally, the agency has conducted the following assurance and advisory services: • Payroll audit and headcount in nineteen (19) covered entities. Collaboration with the Economic and Organised Crime Office (EOCO) on further investigations of financial |  |  |

Internal Audit Agency 18 2022 3rd Quarter Performance Report

| SN | SUB PROGRAMME | ACTIVITIES | BASELINE-2021 | OUTPUT INDICATORS | STATUS | OUTCOME | REMARKS |
| --- | --- | --- | --- | --- | --- | --- | --- |
|  |  |  |  |  | malfeasance in two (2) Covered Entities. |  |  |
| 3. | Technical, Research, Monitoring and Evaluation | Build capacity of staff of IAUs on Working Paper Management |  | Number of Covered Entities trained on Working Paper Management | Training was provided for Seven-Hundred and Eleven (711) public officers from One hundred and seven (108) covered entities in Working Paper Management, Guidelines to handling Audit queries and Contemporary Internal Audit Practice in Public Sector. |  |  |
|  |  |  |  | Number of officers trained on Working Paper Management |  |  |  |
|  |  | Train Audit Committees members in Covered Entities |  | Two hundred (200) Audit Committee Members expected to be trained | Training was provided for Ten(10) Audit Committee members |  |  |
|  |  | Carry out Information System Audit On Site support training for IAUs of Covered Entities |  | Information System Audit On- Site Support Training expected to be conducted for IAUs of Covered Entities | Virtual Training on Information Systems (IS) Audit was provided for Three-Hundred and forty-nine (349) Internal Audit Staff of Covered Entities |  |  |
| 4 | Enterprise Risk Management (ERM) Units | Facilitate the development and institutionalization s of ERM in public sector institutions | 508 officers from 18 covered entities were trained on Enterprise Risk Management. | ERM practice expected to be established in twenty (20) MDAs, MMDA, SOEs and Others | Fourteen (14) Covered Entities made up of three hundred and forty-seven (347) Management and key staff, including staff of the IAUs were trained on ERM. | Build capacity of Covered Entities on Governance, Risk, Control, and effective financial management |  |
|  |  | Build capacity of staff of IAUs on Risk Based Internal Auditing (RBIA) | Three Hundred and Twenty (320) officers eighty-seven (87) covered entities were trained on RBIA | Four hundred (400) Internal Audit Staff expected to be trained on the use of the RBIA Audit Manual | Nine (9) officers from one (1) covered entity have undergone RBIA training |  |  |

Internal Audit Agency 19 2022 3rd Quarter Performance Report

| SN | SUB PROGRAMME | ACTIVITIES | BASELINE-2021 | OUTPUT INDICATORS | STATUS | OUTCOME | REMARKS |
| --- | --- | --- | --- | --- | --- | --- | --- |
| 5 | Project Management | Facilitate and coordinate projects | Four (4) Projects were identified and monitored | Ten (10) projects expected to be identified, monitored and report issued | Two development projects identified and monitored namely: The PFM League Table and the District Accountability Index | Well-coordinated programmes and project and improved relationships with stakeholders |  |
|  |  | Sign and operationalize Memorandum of Understanding (MOU) with Professional and Anti-corruption bodies | Six (6) MOUs were Signed and Operationalized | Ten (10) MOUs expected to be Signed and Operationalized | 3 MOUs signed with professional and anti-corruption bodies |  |  |
| 6 | Human Resource Management and Administration | Negotiate and implement new Conditions of Service (CoS) for the staff of the Agency | N/A | New conditions of Service expected to be negotiated, approved, and implemented | Draft condition of service completed. Awaits the endorsement of the HREC |  |  |
|  |  | Obtain Financial Clearance (FC) for recruitment of new staff | Eleven (11) Financial Clearance were obtained | Twenty (20) Financial Clearance expected to be obtained for the recruitment of additional staff | Request for Financial Clearance has been processed and submitted for approval | Staff strength improved. |  |
|  |  | Capacity Building for IAA staff (Local Training) | Five Capacity building programmes were provided, with 34 employees trained. | Capacity building expected to be provided for Forty (40) staff and Training reports submitted | 19 training programmes carried out with a total of 50 employees trained, with some trained multiple times | Improve upon staff capability |  |
|  |  | Capacity Building for IAA staff (Foreign Training) | Foreign training was put on hold due to COVID 19 restrictions | Capacity building expected to be provided for Five (5) staff and Training reports submitted |  |  |  |
|  |  | Conduct staff Performance Appraisal | Performance Appraisal for 2020 conducted and report issued to the Board of Directors for necessary actions. | Performance Appraisal expected to be conducted and report issued | Performance Appraisal for 2021 conducted and report yet to be submitted to the Board. | Training need of staff assessed |  |
|  |  | Organize in-house lectures and presentations | In-house lectures conducted within the period include | Quarterly in-house lectures and presentations expected | Three In-house lectures and presentation organized. |  |  |

Internal Audit Agency 20 2022 3rd Quarter Performance Report

| SN | SUB PROGRAMME | ACTIVITIES | BASELINE-2021 | OUTPUT INDICATORS | STATUS | OUTCOME | REMARKS |
| --- | --- | --- | --- | --- | --- | --- | --- |
|  |  | using internal and external resource persons | Employee Conditions of Service; Declaration of Assets and Liabilities and Maintenance of new IAA website | to be conducted and report issued |  |  |  |
|  |  | Organise orientation for newly recruited Officers and National Service Personnel | Orientation was conducted for four (4) newly recruited officers. | Newly recruited Officers and Service Personnel posted to the Agency expected to be provided with Orientation and report issued | Orientation was successfully done for 9 newly recruited staff | Integration of staff into the Agency. |  |
|  |  | Payroll Verification and Validation | Monthly Salaries of staff of the Agency Validated | Monthly validation of staff salaries expected to be conducted and report issued | Monthly validation successfully carried out | Staff salary paid. |  |
|  |  | Facilitate staff promotional interviews | Staff promotional Interview conducted and Report discussed by the HREC | Staff promotional Interview expected to be conducted and Report issued | Not Due |  |  |
|  |  | Conduct staff needs Assessment in the IAUs of Covered Entities | N/A | Staff needs assessment of IAUs expected to be conducted and report issued | Questionnaire for staff needs assessment has been reviewed and a plan drawn, awaiting budget release. |  |  |
|  |  | General Administration activities | Quarterly Administrative report issued | Quarterly Administrative activities expected to be Monitored and report issued | 1st,2nd Quarterly Administrative report issued |  |  |
|  |  | Update wireless security | N/A | Wireless access points (Security) expected to be updated | Wireless access points firmware updated and access restricted. | Secured wireless access for staff. |  |
|  |  | Review ICT Policy | N/A | ICT policy expected to be Revised and implemented | Not due |  |  |
|  |  | Conduct succession needs analysis and draw succession plan |  | Succession plan completed | Succession Framework awaits Management’s review and HREC endorsement |  |  |

Internal Audit Agency 21 2022 3rd Quarter Performance Report

| SN | SUB PROGRAMME | ACTIVITIES | BASELINE-2021 | OUTPUT INDICATORS | STATUS | OUTCOME | REMARKS |
| --- | --- | --- | --- | --- | --- | --- | --- |
|  |  | Maintenance of IAA Website | Regular maintenance and update of IAA website carried out | IAA Website expected to be maintained regularly and report issued | Website was updated with PDF reader and Google Forms | Improved visibility and information dissemination on IAA activities |  |
|  |  | Develop Annual Procurement Plan for approval | Annual Procurement Plan developed and approved | Annual Procurement Plan expected to be approved for implementation | Annual procurement plan developed and approved by ETC for implementation | Ensure adherence to statutory requirement. |  |
|  |  | Post Annual Procurement Plan onto Ghaneps | Annual Procurement plan posted on PPA website and copy submitted to PPA | Annual Procurement plan expected to be posted on PPA website and copy submitted to PPA | Procurement Plan has been posted on the GHANEPS website | Ensure adherence to statutory requirement. |  |
|  |  | Quarterly Update of the approved Annual Procurement Plan | Approved Annual Procurement Plan updated quarterly | Annual Procurement plan activities expected to be implemented and report issued | Procurement plan has been updated accordingly |  |  |
|  |  | Implement the approved Annual Procurement Plan | Activities in the approved Annual Procurement plan implemented | Annual Procurement plan activities expected to be implemented and report issued | Implementation of Annual Procurement Plan in progress | Ensure value for money in procurement activities. |  |
|  |  | Management of IAA Stores |  | Regular Management of IAA stores expected to be conducted and quarterly report issued | Receipts into stores and issues out of stores were carried out as per expected procedure |  |  |
|  |  | Conduct Quarterly Stocktaking |  | quarterly stocktaking expected to be conducted and report issued | Quarterly stocktaking conducted, and report issued. |  |  |
| 7 | Corporate Affairs and Communication | Branding of the Agency | N/A | Paneling of walls with pictures of IAA are expected to be carried out | Wall panel completed in February 2022. Paneling to be extended from the walkway to the reception area | Branding of the Agency Funds available to undertake the Agency’s Operational activities |  |
|  |  | Weekly Publication of IAA newsletter | N/A | IAA newsletter expected to published weekly | Fifty-one (51) Weekly IAA newsletters Published. | IAA Board and Internal Stakeholders of the Agency’s awareness of the Agency’s activities. |  |
|  |  | Promoting the Agency’s visibility |  | Four (4) quarterly interviews expected to be granted to the print and electronic media | Interviews granted to the electronic and print media especially in the days preceding |  |  |

Internal Audit Agency 22 2022 3rd Quarter Performance Report

| SN | SUB PROGRAMME | ACTIVITIES | BASELINE-2021 | OUTPUT INDICATORS | STATUS | OUTCOME | REMARKS |
| --- | --- | --- | --- | --- | --- | --- | --- |
|  |  |  |  |  | the 2022 Annual Internal Audit Conference in August |  |  |
|  |  |  |  | Four (4) quarterly visits to selected media houses expected to be conducted. |  |  |  |
|  |  | Communicate with Stakeholders | N/A | Weekly update of information on the Agency’s website expected to be conducted | Regular update of the Agency’s Website and Facebook, Instagram and Twitter pages. | Well-informed Stakeholders On the activities of the Agency | Accessibility to information improved but still room for improvement. |
| 8 | Finance and Corporate Planning | Sourcing and follow up on Releases at the Sector Ministry, MoF, CAGD & DPs | Quarterly follow ups of release received | Four (4) quarterly releases expected to be received | A total of GHc441,009.09 being 1st,2nd & 3rd quarter Goods and Services releases were received through frequent follow ups. (1st QTR= GHc48,911.00 & 2nd QTR=GHc285,098.90) (3rd QTR=GHc107,000.00) | Funds available to undertake the Agency’s Operational activities. |  |
|  |  | Oversee the processing, approval, payment and releases of funds on the GIFMIS Platform | Payment process on the GIFMIS platform were initiated and approved | payment processes on the GIFMIS Platform initiated expected to be approved and released | Payment process on the GIFMIS Platform is completed with the exception of CAPEX |  |  |
|  |  | Prepare Monthly Bank Reconciliation Statements and update cash book. | Monthly Banks reconciliation statement prepared and report issued | Monthly Banks reconciliation statement expected to be prepared and report issued | Bank Reconciliation Statements for January to November prepared and reports issued | Improve financial Control. |  |
|  |  | Finalize Quarterly/ Annual Financial Statements | Quarterly and Annual Financial statements finalized and submitted to CAGD and the IAA governing Board | Quarterly and Annual Financial statements expected to be finalized and submitted to CAGD and the IAA governing Board | Preparation of the 1st, 2nd and 3rd quarter Financial statement completed | Communicate to stakeholders the financial position of the Agency. |  |
|  |  | Initiate the process of appointing External Auditors | The 2020 Financial Statement had been audited by the Auditor General and management letter issued | External Auditors expected to be appointed to Audit 2021 Financial Statements and report submitted to AG and IAA Governing board | External Auditors have commenced audit of 2021 Financial Statements |  |  |

Internal Audit Agency 23 2022 3rd Quarter Performance Report

| SN | SUB PROGRAMME | ACTIVITIES | BASELINE-2021 | OUTPUT INDICATORS | STATUS | OUTCOME | REMARKS |
| --- | --- | --- | --- | --- | --- | --- | --- |
|  |  | Respond to Audit Findings from Internal and External Audit reports | Responses to 3rdquarter Internal Audit Report were provided. | Responses expected to be provided to Audit findings | Responses for audit recommendations contained in the 4th quarter Internal Audit Report were provided. |  |  |
|  |  | Facilitate the completion of input forms in relations to staff recruitment, retirement and resignation | The Input forms for the Deputy Director General, Director Operations, Director HRM & Admin and Senior Manager PBME and Legal Officer were completed and submitted to the Office of the Head Civil Service for processing. | Number of input forms initiated | The Input forms for the newly recruited and promoted staffs were completed and submitted to the Office of the Head Civil Service for necessary action. | Remuneration of staff is assured. |  |
|  |  | Monitoring and Evaluation of the Agency’s projects and programmes | Monitoring and Evaluation of the Agency’s programmes carried out for the 1st quarter Annual monitoring and evaluation yet to carried out | Quarterly Report on Status of Implementation of the Agency’s project and programmes | Mid-Year Monitoring and Evaluation report prepared and submitted and approved for submission | Ensure adherence to the Agency’s mandate and statutory requirement. |  |
|  |  | Collate and consolidated divisional report into the Agency’s Annual Report for onwards submission to the Director General. | 2021 Annual Report Prepared and submitted to the DG | 2022 Annual Report expected to be prepared and submitted to the DG | Annual report submitted and awaiting approval |  |  |
|  |  | Collate and consolidate the Agency’s Quarterly report for onwards Submission to the OoP | 3rd Quarter Budget Performance Report prepared and submitted to the Office of the President (OoP). | 2022 Quarterly Performance Reports expected to be prepared and submitted to the OoP | 1st and 2nd Quarter Budget Performance Report and Mid Year Fiscal Policy Report prepared and submitted to the Office of the President (OoP). 3rd Quarter Budget and Performance Report prepared yet to be sent to the DG for approval. |  |  |

Internal Audit Agency 24 2022 3rd Quarter Performance Report

| SN | SUB PROGRAMME | ACTIVITIES | BASELINE-2021 | OUTPUT INDICATORS | STATUS | OUTCOME | REMARKS |
| --- | --- | --- | --- | --- | --- | --- | --- |
|  |  | Collate and consolidate the Agency’s Annual Workplan/Action Plan | 2022 Workplan/Action plan approved and submitted to OoP | 2023 Workplan expected to be prepared and submitted for approval | 2023 Action Plan yet to be submitted |  |  |
|  |  | Collate and consolidate the Agency’s Annual Budget | 2022 Annual Budget approved for implementation | 2023 Annual Budget expected to be approved for implementation | 2023 Budget approved for implementation |  |  |
|  |  | Facilitate the Development of 2023-2027 Strategic Plan | N/A | 2023-2027 Strategic Plan Developed for Approval | Roadmap for 2023-2027 Strategic Plan Developed. First stage of 2023-2027 Strategic Plan Executed. |  |  |

APPENDIX II - SYSTEMIC ISSUES

| SYSTEMIC ISSUE | ISSUE | AMOUNT GH¢ |
| --- | --- | --- |
| Procurement | Failure to Engage in Competitive Tendering | 2,697,449.75 |

Internal Audit Agency 25 2022 3rd Quarter Performance Report

|  | Failure to route Purchases through Stores | 2,555,776.32 |
| --- | --- | --- |
|  | Purchases from Non-VAT Registered Entities | 1,051,971.05 |
|  | Procurement Above Entity Threshold | 331,499.91 |
|  | Others | 221,692,549.96 |
|  | TOTAL | 228,329,246.99 |
| Cash Management | Expenditure without Warrant | 3,188,679.26 |
|  | Failure to Support PVs with relevant receipts, documents | 9,481,277.25 |
|  | Failure to Retire Imprest/ Disbursements | 2,585,293.49 |
|  | Failure to Account for Revenue Collected | 1,007,168.53 |
|  | Non-acknowledgement of Payment Vouchers by Payees | 1,727,648.30 |
|  | Failure To bank revenue within 24 hrs | 676,608.05 |
|  | Unaccounted Payment Vouchers | 1,006,051.07 |
|  | Failure to submit payment vouchers for pre audit | 7,115,068.34 |
|  | Unauthorized Payment Vouchers | 2,557,274.65 |
|  | Unaccounted Value Books | 13,844.00 |
|  | Fuel Coupons Not Accounted For | 12,350.00 |
|  | Payment not processed through GIFMIS | 1,347,864.25 |
|  | Others | 134,195,010.40 |
|  | TOTAL | 178,610,174.76 |
| Contract | Contracts Not Approved | 2,004,526.80 |
|  | Abandoned Projects | 862,240,636.61 |
|  | Delay in Completion of Projects | 50,150,959.70 |
|  | Others | 6,701,231.17 |
|  | TOTAL | 921,097,354.28 |
| Payroll | Non-Recovery of Salary Advance | 418,521.13 |
|  | Failure To Pay SSNIT Contributions | 235,229.96 |
|  | Unearned Salary | 359,334.33 |
|  | Others | 286,014.94 |
|  | TOTAL | 1,299,100.36 |
| Tax | Non-Remittance of Withholding Tax | 47,310,335.90 |
|  | Failure to Withhold Tax | 187,365.98 |
|  | Others | 122,257.56 |

Internal Audit Agency 26 2022 3rd Quarter Performance Report

|  | TOTAL | 47,619,959.44 |
| --- | --- | --- |
| Others | Failure to Log/ account for Fuel Purchases | 361,796.56 |
|  | Failure to Retrieve Debt | 450,908,080.60 |
|  | Others | 292,388.50 |
|  | TOTAL | 460,775,034.58 |
| GRAND TOTAL |  | 1,837,730,870.41 |

APPENDIX III: Details of Training Provided for the period 1st January to 0th December 2022

| Training Area | # | Names of Covered Entities | Categories of Officers | Dates | Training Venue | Attendance |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- |
|  |  |  |  |  |  | Male | Female | Total |
| ERM | 1 | Energy Commission | Management & IAU Staff | 21st-22nd February 2022 | City Escape Hotel | 20 | 14 | 34 |
| ERM | 2 | Internal Audit Agency | Management & IAU Staff | 1st – 4th March 2022 | IAA Office | 19 | 15 | 34 |
| ERM | 3 | Securities & Exchange Commission | Management & IAU Staff | 14th- 17th March 2022 | Mensvic Hotel | 10 | 3 | 13 |
| ERM | 4 | Ghana Institute of Languages | Management & IAU Staff | 22nd – 25th March 2022 | GIL Head Office | 15 | 7 | 22 |
| ERM | 5 | National Communications Authority | Management & IAU Staff | 11th- 14th April 2022 | NCA Head Office | 12 | 6 | 18 |
| ERM | 6 | NADMO | Management & IAU Staff | 10th – 13th May 2022 | ILGS | 13 | 3 | 16 |
| ERM | 7 | Ghana Airports Company Limited | Management & IAU Staff | 23rd – 26th May 2022 | GACL Head Office | 27 | 9 | 36 |
| ERM | 8 | Environmental Protection Agency | Management & IAU Staff | 31st May - 3rd June 2022 | EPA Head Office | 12 | 5 | 17 |
| RBIA | 9 | Environmental Protection Agency | IAU Staff | 14th-17th June 2022 | EPA Head Office | 7 | 2 | 9 |
| ERM | 10 | Middle Development Authority | Management & IAU Staff | 18th- 22nd July 2022 | Anita Hotel | 12 | 5 | 17 |
| ERM | 11 | Environmental Protection Agency | Management & IAU Staff | 1st – 4th August 2022 | IES Office | 24 | 15 | 39 |
| ERM | 12 | Petroleum Commission | Management & IAU Staff | 23rd-26th August 2022 | PC Head Office | 8 | 2 | 10 |
| ERM | 13 | Ministry of Foreign Affairs & Reg. In. | Management & IAU Staff | 30th Aug – 2nd Sep. 2022 | MFARI Head Office | 34 | 33 | 67 |
| ERM | 14 | Energy Commission | Board & Management | 5th – 6th October 2022 | EC Head Office | 8 | 7 | 15 |
| Training Area | # | Names of Covered Entities | Categories of Officers | Dates | Training Venue | Attendance |  |  |
|  |  |  |  |  |  | Male | Female | Total |
| RBIA | 14 | Environmental Protection Agency | IAU Staff | 14th-17th June 2022 | EPA Head Office | 7 | 2 | 9 |
| TOTALS |  |  |  |  |  |  |  | 356 |
| Training Area | # | Names of Covered Entities | Categories of Officers | Dates | Training Venue | Attendance |  |  |
|  |  |  |  |  |  | Male | Female | Total |
|  | 1 | Biakoye District Assembly | Management & IAU Staff | 28th March 2022 | Hill View Hotel | 3 | 0 | 3 |
|  | 2 | Kadjebi District Assembly | Management & IAU Staff | 28th March 2022 | Hill View Hotel | 3 | 0 | 3 |
|  | 3 | Hohoe Municipal Assembly | Management & IAU Staff | 28th March 2022 | Hill View Hotel | 2 | 0 | 2 |

Internal Audit Agency 27 2022 3rd Quarter Performance Report

| Working Papers | 4 | Ho Municipal Assembly | Management & IAU Staff | 28th March 2022 | Hill View Hotel | 3 | 0 | 3 |
| --- | --- | --- | --- | --- | --- | --- | --- | --- |
|  | 5 | La Dade Kotopon Municipal Assembly | Management & IAU Staff | 28th March 2022 | Hill View Hotel | 3 | 1 | 4 |
|  | 6 | Ga East Municipal Assembly | Management & IAU Staff | 28th March 2022 | Hill View Hotel | 2 | 2 | 4 |
|  | 7 | Weija-Gbawe Municipal Assembly | Management & IAU Staff | 28th March 2022 | Hill View Hotel | 2 | 0 | 2 |
|  | 8 | New Juaben North Municipal Assembly | Management & IAU Staff | 28th March 2022 | Hill View Hotel | 2 | 0 | 2 |
|  | 9 | Birm North District Assembly | Management & IAU Staff | 28th March 2022 | Hill View Hotel | 2 | 0 | 2 |
|  | 10 | Ketu South Municipal Assembly | Management & IAU Staff | 28th March 2022 | Hill View Hotel | 3 | 0 | 3 |
|  | 11 | Birim Central Akim-Oda | Management & IAU Staff | 28th March 2022 | Hill View Hotel | 2 | 0 | 2 |
|  | 12 | NingoPrampram District Assembly | Management & IAU Staff | 28th March 2022 | Hill View Hotel | 3 | 0 | 3 |
|  | 13 | Volta RCC | Management & IAU Staff | 28th March 2022 | Hill View Hotel | 1 | 0 | 1 |
|  | 14 | Oti RCC | Management & IAU Staff | 28th March 2022 | Hill View Hotel | 1 | 0 | 1 |
|  | 15 | RCC, Accra | Management & IAU Staff | 28th March 2022 | Hill View Hotel | 2 | 0 | 2 |
|  | 16 | New Juaben South Municipal Assembly | Management & IAU Staff | 28th March 2022 | Hill View Hotel | 1 | 0 | 1 |
|  | 17 | Ga South Municipal Assembly | Management & IAU Staff | 28th March 2022 | Hill View Hotel | 2 | 0 | 2 |
|  | 18 | Adentan Municipal Assembly | Management & IAU Staff | 28th March 2022 | Hill View Hotel | 3 | 1 | 4 |
|  | 19 | South Tongu District Assembly | Management & IAU Staff | 28th March 2022 | Hill View Hotel | 2 | 1 | 3 |
|  | 20 | Suhum Municipal Assembly | Management &IAU Staff | 28th March 2022 | Hill View Hotel | 2 | 0 | 2 |
|  | 21 | Abukwa North Municipal Assembly | Management &IAU Staff | 28th March 2022 | Hill View Hotel | 2 | 1 | 3 |
| TOTALS |  |  |  |  |  |  |  | 52 |
| Training Area | # | Names of Covered Entities | Categories of Officers | Dates | Training Venue | Attendance |  |  |
|  |  |  |  |  |  | Male | Female | Total |
|  | 1 | Nkoranza South Municipal Assembly | Management & IAU Staff | 4th April, 2022 | Crystal Rose Ambassador Hotel |  | 3 0 | 3 |
|  | 2 | Kwadaso Municipal Assembly | Management & IAU Staff | 4th April, 2022 | Crystal Rose Ambassador Hotel | 3 | 1 | 3 |
|  | 3 | Ejisu Municipal Assembly | Management & IAU Staff | 4th April, 2022 | Crystal Rose Ambassador Hotel | 3 | 0 | 3 |
|  | 4 | Techniman Municipal Assembly | Management & IAU Staff | 4th April, 2022 | Crystal Rose Ambassador Hotel | 3 | 0 | 3 |
|  | 5 | Bono East RCC | Management & IAU Staff | 4th April, 2022 | Crystal Rose Ambassador Hotel | 1 | 0 | 1 |
|  | 6 | Sunyani Municipal Assembly | Management & IAU Staff | 4th April, 2022 | Crystal Rose Ambassador Hotel | 3 | 0 | 3 |
|  | 7 | Banda District Assembly | Management & IAU Staff | 4th April, 2022 | Crystal Rose Ambassador Hotel | 4 | 0 | 4 |

Internal Audit Agency 28 2022 3rd Quarter Performance Report

| Working Papers | 8 | Asunafo South District Assembly | Management & IAU Staff | 4th April, 2022 | Crystal Rose Ambassador Hotel | 2 | 0 | 2 |
| --- | --- | --- | --- | --- | --- | --- | --- | --- |
|  | 9 | BosomeFreho District Assembly | Management & IAU Staff | 4th April, 2022 | Crystal Rose Ambassador Hotel | 1 | 0 | 1 |
|  | 10 | Ahafo RCC | Management & IAU Staff | 4th April, 2022 | Crystal Rose Ambassador Hotel | 1 | 0 | 1 |
|  | 11 | Wenchi Municipal Assembly | Management & IAU Staff | 4th April, 2022 | Crystal Rose Ambassador Hotel | 3 | 1 | 4 |
|  | 12 | Bono RCC | Management & IAU Staff | 4th April, 2022 | Crystal Rose Ambassador Hotel | 1 | 0 | 1 |
|  | 13 | Obuasi Municipal Assembly | Management & IAU Staff | 4th April, 2022 | Crystal Rose Ambassador Hotel | 3 | 0 | 3 |
|  | 14 | BosomtweDistict Assembly | Management & IAU Staff | 4th April, 2022 | Crystal Rose Ambassador Hotel | 1 | 0 | 1 |
|  | 15 | Tain District Assembly | Management & IAU Staff | 4th April, 2022 | Crystal Rose Ambassador Hotel | 2 | 0 | 2 |
|  | 16 | Asokwa Municipal Assembly | Management & IAU Staff | 4th April, 2022 | Crystal Rose Ambassador Hotel | 3 | 0 | 3 |
|  | 17 | Ashanti ARCC | Management & IAU Staff | 4th April, 2022 | Crystal Rose Ambassador Hotel | 0 | 2 | 2 |
|  | 18 | Kumasi Metropolitan Assembly | Management & IAU Staff | 4th April, 2022 | Crystal Rose Ambassador Hotel | 4 | 0 | 4 |
|  | 19 | Asutifi South District Assembly | Management & IAU Staff | 4th April, 2022 | Crystal Rose Ambassador Hotel | 1 | 0 | 1 |
| TOTALS |  |  |  |  |  |  |  | 45 |
| Training Area | # | Names of Covered Entities | Categories of Officers | Dates | Training Venue | Attendance |  |  |
|  |  |  |  |  |  | Male | Female | Total |
|  | 1 | KassenaNankana West District Assembly | Management & IAU Staff | 30th May – 3rd June 2022 | Global Dream Hotel | 3 | 1 | 4 |
|  | 2 | Lawra District Assembly | Management & IAU Staff | 30th May – 3rd June 2022 | Global Dream Hotel | 2 | 0 | 2 |
|  | 3 | Bongo District Assembly | Management & IAU Staff | 30th May – 3rd June 2022 | Global Dream Hotel | 3 | 0 | 3 |
|  | 4 | KassenaNankana Municipal Assembly | Management & IAU Staff | 30th May – 3rd June 2022 | Global Dream Hotel | 3 | 0 | 3 |
|  | 5 | Bawku West District Assembly | Management & IAU Staff | 30th May – 3rd June 2022 | Global Dream Hotel | 1 | 1 | 2 |
|  | 6 | Bolga East District Assembly | Management & IAU Staff | 30th May – 3rd June 2022 | Global Dream Hotel | 3 | 0 | 3 |

Internal Audit Agency 29 2022 3rd Quarter Performance Report

| Working Papers | 7 | Bolga Municipal Assembly | Management & IAU Staff | 30th May – 3rd June 2022 | Global Dream Hotel | 3 | 0 | 3 |
| --- | --- | --- | --- | --- | --- | --- | --- | --- |
|  | 8 | Kassena Nankana East District Assembly | Management & IAU Staff | 30th May – 3rd June 2022 | Global Dream Hotel | 1 | 0 | 1 |
|  | 9 | Upper East RCC | Management & IAU Staff | 30th May – 3rd June 2022 | Global Dream Hotel | 1 | 0 | 1 |
|  | 10 | Jirapa Municipal Assembly | Management & IAU Staff | 30th May – 3rd June 2022 | Global Dream Hotel | 4 | 0 | 4 |
|  | 11 | Lawra Municipal Assembly | Management & IAU Staff | 30th May – 3rd June 2022 | Global Dream Hotel | 3 | 0 | 3 |
|  | 12 | Nadwoli-Kaleo District Assembly | Management & IAU Staff | 30th May – 3rd June 2022 | Global Dream Hotel | 2 | 0 | 2 |
|  | 13 | Nandom Municipal Assembly | Management & IAU Staff | 30th May – 3rd June 2022 | Global Dream Hotel | 2 | 1 | 3 |
|  | 14 | Wa Municipal Assembly | Management & IAU Staff | 30th May – 3rd June 2022 | Global Dream Hotel | 5 | 1 | 6 |
|  | 15 | Upper West RCC | Management & IAU Staff | 30th May – 3rd June 2022 | Global Dream Hotel | 2 | 0 | 0 |
|  | 16 | Gushegu Municipal Assembly | Management & IAU Staff | 30th May – 3rd June 2022 | Global Dream Hotel | 2 | 0 | 2 |
|  | 17 | Savelugu Municipal Assembly | Management & IAU Staff | 30th May – 3rd June 2022 | Global Dream Hotel | 3 | 0 | 3 |
|  | 18 | Tamale Metro. Assembly | Management & IAU Staff | 30th May – 3rd June 2022 | Global Dream Hotel | 2 | 1 | 3 |
|  | 19 | North East RCC | Management & IAU Staff | 30th May – 3rd June 2022 | Global Dream Hotel | 1 | 0 | 1 |
|  | 20 | Bole District Assembly | Management & IAU Staff | 30th May – 3rd June 2022 | Global Dream Hotel | 3 | 0 | 3 |
|  | 21 | Garu District Assembly | Management & IAU Staff | 30th May – 3rd June 2022 | Global Dream Hotel | 2 | 0 | 2 |
|  | 22 | Northern RCC | Management & IAU Staff | 30th May – 3rd June 2022 | Global Dream Hotel | 2 | 0 | 2 |
|  | 23 | Central Gonja District Assembly | Management & IAU Staff | 30th May – 3rd June 2022 | Global Dream Hotel | 1 | 0 | 1 |
| TOTALS |  |  |  |  |  |  |  | 59 |
| Training Area | # | Names of Covered Entities | Categories of Officers | Dates | Training Venue | Attendance |  |  |
|  |  |  |  |  |  | Male | Female | Total |
|  | 1 | Twifo/AtiMorkwa District Assembly | Management & IAU Staff | 16th June 2022 | Riverside Bridge Hotel | 1 | 0 | 1 |

Internal Audit Agency 30 2022 3rd Quarter Performance Report

| Working Papers | 2 | Komenda-Edina-Eguafo-Abrim Municipal Assembly | Management & IAU Staff | 16th June 2022 | Riverside Bridge Hotel | 1 | 0 | 1 |
| --- | --- | --- | --- | --- | --- | --- | --- | --- |
|  | 3 | Gomoa District Assembly | Management & IAU Staff | 16th June 2022 | Riverside Bridge Hotel | 1 | 0 | 1 |
|  | 4 | Aowin District Assembly | Management & IAU Staff | 16th June 2022 | Riverside Bridge Hotel | 2 | 0 | 2 |
|  | 5 | Suaman District Assembly | Management & IAU Staff | 16th June 2022 | Riverside Bridge Hotel | 1 | 0 | 1 |
|  | 6 | Western Region RCC | Management & IAU Staff | 16th June 2022 | Riverside Bridge Hotel | 1 | 0 | 1 |
|  | 7 | Central Region RCC | Management & IAU Staff | 16th June 2022 | Riverside Bridge Hotel | 2 | 0 | 2 |
|  | 8 | Bibiani – AnhwiasoBekwaiMunicipal Assembly | Management & IAU Staff | 16th June 2022 | Riverside Bridge Hotel | 1 | 0 | 1 |
|  | 9 | Prestea Huni Valley District Assembly | Management & IAU Staff | 16th June 2022 | Riverside Bridge Hotel | 1 | 0 | 1 |
|  | 10 | Awutu Senya East Municipal Assembly | Management & IAU Staff | 16th June 2022 | Riverside Bridge Hotel | 1 | 0 | 1 |
|  | 11 | Cape Coast Metro. Assembly | Management & IAU Staff | 16th June 2022 | Riverside Bridge Hotel | 1 | 0 | 1 |
|  | 12 | Nzema East Municipal Assembly | Management & IAU Staff | 16th June 2022 | Riverside Bridge Hotel | 1 | 0 | 1 |
|  | 13 | TarkwaNsuaem Municipal Assembly | Management & IAU Staff | 16th June 2022 | Riverside Bridge Hotel | 1 | 0 | 1 |
| TOTALS |  |  |  |  |  |  |  | 15 |
| Training Area | # | Names of Covered Entities | Categories of Officers | Dates | Training Venue | Attendance |  |  |
|  |  |  |  |  |  | Male | Female | Total |
| Working Papers | 1 | Electoral Commission | Accounts, HR, Proc. & IAU Staff | 20th June-1st July 2022 | EC’s Conference room | 2 | 9 | 11 |
| TOTALS |  |  |  |  |  |  |  | 11 |
| Training Area | # | Names of Covered Entities | Categories of Officers | Dates | Training Venue | Attendance |  |  |
|  |  |  |  |  |  | Male | Female | Total |
| Audit Committe e | 1 | Accra Technical University | Audit Committee Members | 22nd June | ATU’s Council room | 6 | 4 | 10 |
| TOTALS |  |  |  |  |  |  |  | 10 |

Internal Audit Agency 31 2022 3rd Quarter Performance Report

| Training Area | # | Names of Covered Entities | Categories of Officers | Dates | Training Venue | Attendance |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- |
|  |  |  |  |  |  | Male | Female | Total |
| Guideline s to Handling Audit Queries | 1 | National Petroleum Authority | Executive Committee Members | 27th June | Best Western Premier Hotel | 10 | 8 | 18 |
| TOTALS |  |  |  |  |  |  |  | 18 |
| Training Area | # | Names of Covered Entities | Categories of Officers | Dates | Training Venue | Attendance |  |  |
|  |  |  |  |  |  | Male | Female | Total |
| Working Papers | 1 | Jasikan District Assembly | IAU staff | 23rd- 24th August 2022 | ORCC Conf.room | 1 | 2 | 3 |
|  | 2 | Biakoye District Assembly | IAU staff | 23rd- 24th August 2022 | ORCC Conf.room | 8 | 0 | 8 |
|  | 3 | Nkwanta South Municipal Assembly | IAU staff | 23rd- 24th August 2022 | ORCC Conf.room | 5 | 1 | 6 |
|  | 4 | Kadjebi District Assembly | IAU staff | 23rd- 24th August 2022 | ORCC Conf.room | 6 | 0 | 6 |
|  | 5 | Guan District Assembly | IAU staff | 23rd- 24th August 2022 | ORCC Conf.room | 3 | 0 | 3 |
|  | 6 | Krachi East Municipal Assembly | IAU staff | 23rd- 24th August 2022 | ORCC Conf.room | 5 | 0 | 5 |
|  | 7 | Krachi Nchumuru District Assembly | IAU staff | 23rd- 24th August 2022 | ORCC Conf.room | 4 | 0 | 4 |
|  | 8 | Krachi west Municipal Assembly | IAU staff | 23rd- 24th August 2022 | ORCC Conf.room | 3 | 0 | 3 |
|  | 9 | Oti Regional Coordinating Council | IAU staff | 23rd- 24th August 2022 | ORCC Conf.room | 7 | 4 | 11 |
|  | 10 | Nkwanta North District Assembly | IAU staff | 23rd- 24th August 2022 | ORCC Conf.room | 4 | 0 | 4 |
|  | 11 | Regional Education Office | IAU staff | 23rd- 24th August 2022 | ORCC Conf.room | 1 | 0 | 1 |
| TOTALS |  |  |  |  |  |  |  | 54 |
| Training Area | # | Names of Covered Entities | Categories of Officers | Dates | Training Venue | Attendance |  |  |
|  |  |  |  |  |  | Male | Female | Total |
|  | 1 | Ketu South Municipal | IAU Staff | 25th- 26th August 2022 | Residency Conf. Hall of the VRCC | 3 | 1 | 4 |
|  | 2 | Hohoe Municipal Assembly | IAU Staff | 25th- 26th August 2022 | Residency Conf. Hall of the VRCC | 3 | 3 | 6 |
|  | 3 | Ketu North Municipal assembly | IAU Staff | 25th- 26th August 2022 | Residency Conf. Hall of the VRCC | 2 | 1 | 3 |
|  | 4 | Ho-west District Assembly | IAU Staff | 25th- 26th August 2022 | Residency Conf. Hall of the VRCC | 1 | 3 | 4 |
|  | 5 | South Tongu District Assembly | IAU Staff | 25th- 26th August 2022 | Residency Conf. Hall of the VRCC | 1 | 4 | 5 |
|  | 6 | Agortime- ziope | IAU Staff | 25th- 26th August 2022 | Residency Conf. Hall of the VRCC | 2 | 2 | 4 |

Internal Audit Agency 32 2022 3rd Quarter Performance Report

| Working Papers | 7 | South Dayi Assembly | IAU Staff | 25th- 26th August 2022 | Residency Conf. Hall of the VRCC | 2 | 1 | 3 |
| --- | --- | --- | --- | --- | --- | --- | --- | --- |
|  | 8 | Volta Regional coordinating council | IAU Staff | 25th- 26th August 2022 | Residency Conf. Hall of the VRCC | 9 | 0 | 9 |
|  | 9 | Akatsi North District Assembly | IAU Staff | 25th- 26th August 2022 | Residency Conf. Hall of the VRCC | 1 | 1 | 1 |
|  | 10 | Afadzato South District Assembly | IAU Staff | 25th- 26th August 2022 | Residency Conf. Hall of the VRCC | 3 | 0 | 3 |
|  | 11 | Keta Municipal Assembly | IAU Staff | 25th- 26th August 2022 | Residency Conf. Hall of the VRCC | 3 | 0 | 3 |
|  | 12 | North Tongu District | IAU Staff | 25th- 26th August 2022 | Residency Conf. Hall of the VRCC | 5 | 1 | 6 |
|  | 13 | Ho Municipal Assembly | IAU Staff | 25th- 26th August 2022 | Residency Conf. Hall of the VRCC | 2 | 4 | 6 |
|  | 14 | Adakl;u District Assembly | IAU Staff | 25th- 26th August 2022 | Residency Conf. Hall of the VRCC | 0 | 1 | 1 |
|  | 15 | Anloga District Assembly | IAU Staff | 25th- 26th August 2022 | Residency Conf. Hall of the VRCC | 3 | 1 | 4 |
|  | 16 | North Dayi District Asssembly | IAU Staff | 25th- 26th August 2022 | Residency Conf. Hall of the VRCC | 4 | 0 | 4 |
|  | 17 | Akatsi South Municipal Assembly | IAU Staff | 25th- 26th August 2022 | Residency Conf. Hall of the VRCC | 1 | 2 | 3 |
| TOTALS |  |  |  |  |  |  |  | 69 |
| Training Area | # | Names of Covered Entities | Categories of Officers | Dates | Training Venue | Attendance |  |  |
|  |  |  |  |  |  | Male | Female | Total |
| Overview of IS Audit | 1 | Public Institutions | Internal auditors | 7th September 2022 | Virtual | - | - | 349 |
| TOTALS |  |  |  |  |  |  |  | 349 |

Internal Audit Agency 33 2022 3rd Quarter Performance Report