|  | 1.2 ANTI-MONEY LAUNDERING AND COMBATING TERRORISM FINANCING (AML/CTF) |  |  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- |
| COMMITMENT/MILESTONES | INDICATOR | DEFINITION | BASELINE 2021 | END TARGET 2023 | PROGRESS AS AT JUNE 2023 | MEANS OF VERIFICATION | REMARKS (NEXT STEPS) | RESPONSIBILITY |
| Commitment 1.2 .1: To effectively implement the Anti-Money Laundering Act, 2020 (Act 1044) to ensure that Ghana does not get blacklisted again for lapses in the country’s AML/CTF regime. | Number of reported cases of money laundering by FIC, EOCO | Measures cases of money laundering as defined in the Money Laundering Act, 2020 (Act 1044) | 2,970 number of reported cases of money laundering in 2021 | 3,100 number of reported cases of money laundering in 2023 | 1,050 number of reported cases filed with the FIC as at June 30, 2023. | Periodic Reports |  | Lead MDAs Financial Intelligence Centre (FIC), Other State Actors Economic and Organized Crime Office (EOCO), Ghana Audit Service. Collaborating institutions Ghana Anti-Corruption Coalition (GACC), Ghana Integrity Initiative (GII), Centre\ for Democratic Development (CDD). Institute for Democratic Governance (IDEG), Commonwealth Human Rights Initiative (CHRI), West African Civil Society Institute (WACSI). |
| Milestones Activities 1.2.1.1: Government to establish the Board and committees of FIC | Board and Committees of FIC have been established. (Yes) | Indicator verifies the establishment of Board and Committees of FIC | No | Yes |  | Board Minutes |  |  |
| 1.2.1.2: Parliament to pass Legislative Instrument for Anti-Money Laundering Act, 2020 (Act 1044) | Parliament has passed the Legislative Instrument for Anti-Money Laundering Act, 2020 (Act 1044) (No) | Measure verifies the status of the passing of the Anti-Money Laundering Act by parliament | No | Yes | On-going | AML Regulations | On-going |  |
| 1.2.1.3: FIC to publish annually reports on implementation of Act, 2020 (Act 1044) | Annual Reports on implementation of Act, 2020 (Act 1044) published by FIC | The report details the progress of implementation of the Act,2020 | No report on the implementation of Act, 2020 (Act1044) has been published | Annual reports on implementation of Act, 2020 (Act 1044) published and disseminated. | Draft reports under review | Annual Reports | 2020-2022 draft reports currently under review. |  |
| 1.2.1.4: FIC to engage CSOs and other stakeholders on implementation of Act | FIC has engaged CSOs and other stakeholder in the implementation of Act with written reports of the engagements. (Yes) | The indicator captures the number, frequency, and kinds of engagements with CSOs and other stakeholders on the implementation of Act 1044 | No | Yes | Continuous engagement with the CSOs | Training Reports | The Centre continues to engage all the relevant stakeholders in the fight against money laundering and terrorism financing including the CSOs. It has conducted a number of outreach programmes with the Non-Profit Organisation Secretariat (NPOS) and Institute for Democratic Governance (IDEG) in Accra, Tamale, Kumasi, Takoradi and Koforidua. | . |