|  | 2.2 OPEN AND TRANSPARENT TRACKING OF PUBLIC INVESTMENTS |  |  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- |
| COMMITMENTS/ MILESTOES | INDICATOR | DEFINITION | BASELINE 2021 | END TARGET 2023 | PROGRESS AS AT JUNE, 2023 | MEANS OF VERIFICATION | REMARKS (NEXT STEPS) | RESPONSIBILITY |
| Commitment 2.2.1: - SIGA to publish by December 2022 the register of specified entities in which the state has interest. - Publish evaluation reports. - Develop code of corporate governance. | Register of specified entities in which the state has interest published by SIGA Evaluations conducted and reports published |  |  |  |  |  |  | Responsible MDAs State Interests and Governance Authority (SIGA) Other State Actor Ministry of Finance and Collaborating Institutions Center for Budget Advocacy (CBA) Ghana Integrity Initiative (GII) Institute for Economic Affairs (IEA) Institute for Fiscal Studies (IFS) Center for Democratic Development (CDD) and Ghana Anti-Corruption Initiative (GAI) |
| Milestones Activities 2.2.1.1: Register of entities in which state has interest published by SIGA by December 2022 | SIGA has published register of entities of interest to the state published by (Yes, No) | The register provides details of entities of interest to the state | No | Yes | Fully achieved | List published on www.siga.gov.gh https://siga.gov.gh/specified-entities-list/ |  |  |
| 2.2.1.2: Evaluation reports of public entities published by January 2023 | SIGA has published evaluation reports of public entities (Yes, No) |  | No | Yes | Fully achieved for 2020 | Published in the 2020 State Ownership Report on www.mofep.gov.gh | Currently working on the 2021 |  |
| 2.2.1.3: Code of corporate governance developed by January 2023 | SIGA has developed the Code of Corporate Governance (Yes, No) |  | No | Yes |  |  |  |  |